## Deliverables
Deliverables for Project
Deliverables
Work Package No | Deliverable Related No | Deliverable No |  | Deliverable Name | Lead Beneficiary | Type | Dissemination Level | Due Date | New Due Date (if delay) | Delivery Date | Approval Date | Status
WP1 | D1.1 | D1 | Contractual Procedure | Officially signed documents (2) (Grant Agreement/Partnership Agreement) | KMM | R | SEN | 31 Jan 2023 |  | 30 Jan 2023 | 06 Jul 2023 | Approved
WP1 | D1.2 | D2 | Project Committees | No of Committees (3) | KMM | R | SEN | 31 Jan 2023 |  | 30 Jan 2023 | 06 Jul 2023 | Approved
WP2 | D2.1 | D3 | Multilevel Actors Workshops | Events, Particant List, Photos, Videos, Minutes in _en | KMM | OTHER | PU | 31 May 2023 |  | 13 Jul 2023 | 01 Mar 2024 | Approved
WP2 | D2.2 | D4 | Crash Course in the Interpretation of Heritage | Course Guidelines, 4 Modules in .pdf form, Video Recordings; Participant Lists, ppt presentations; Checklists; 4 web-based tutorials in _en. | ARF | OTHER | PU | 30 Sep 2023 |  | 30 Sep 2023 | 01 Mar 2024 | Approved
WP2 | D2.3 | D5 | Web-based Tutorials in Tourism Planning | Course Guidelines, 4 Modules in .pdf form, Videos, ppt presentations; Checklists; 4 web-based tutorials in _en. | Eduagility | OTHER | PU | 31 May 2024 |  | 30 May 2024 |  | Submitted
WP3 | D3.1 | D6 | The TOURBINE Virtual Desk and Knowledge Toolkit | 4 web-based platforms in _en | Eduagility | OTHER | PU | 31 Dec 2024 |  |  |  | Pending
WP3 | D3.2 | D7 | Study Visits and Evaulation Workshops, Educational AV Record | 8 Training Sessions in TR/RO/GR/DE and 20 Training Packs in multimedia formats | Eduagility | OTHER | PU | 30 Nov 2024 |  | 29 Nov 2024 |  | Submitted
WP3 | D3.3 | D8 | Crash Course in the Gamification of Heritage | 4 onsite training sessions in _en 4 Training Packs in multimedia formats | Eduagility | OTHER | PU | 30 Nov 2024 |  | 29 Nov 2024 |  | Submitted
WP4 | D4.1 | D9 | The Experience-based Route | Web-based application in_en; _.pdf documentation | ARF | DEM | PU | 29 Feb 2024 |  | 14 Apr 2024 |  | Submitted
WP4 | D4.2 | D10 | Heritage Games | Web-based application in_en; _.pdf documentation | Eduagility | DEM | PU | 31 Jul 2024 |  | 29 Jul 2024 |  | Submitted
WP4 | D4.3 | D11 | Community-based Tourism App | Web-based application in_en | Eduagility | DEM | PU | 30 Sep 2024 |  | 29 Sep 2024 |  | Submitted
WP4 | D4.4 | D12 | Evaluation Reports | _.pdf documentation | JYIF | R | SEN | 31 Dec 2024 |  |  |  | Pending
WP4 | D4.5 | D13 | The Open Digital Badge | Microcredentials verification in secured png format_in en Microcredentials verification in secured pdf format_in en | Eduagility | OTHER | PU | 31 May 2024 |  | 31 May 2024 |  | Submitted
WP4 | D4.6 | D14 | Field Exercise at the ITB BERLIN 2023 | Event in_en (Minutes, Participant List; Fotos, Videos) | KMM | OTHER | PU | 31 Dec 2024 |  |  |  | Pending
WP4 | D4.7 | D15 | The TOURBINE Observatory | Statutes in _en in _.pdf documentation | KMM | OTHER | PU | 31 Dec 2024 |  |  |  | Pending
WP5 | D5.1 | D16 | Communication Tools (Website; Newsletters; Factsheets; CDV Plan; Spot; Social media Campaign) | No of Tools (6) | KMM | DEC | PU | 31 Dec 2024 |  |  |  | Pending
WP5 | D5.2 | D17 | Communication Events (6 Info Days; 6 Press Conferences; International Conference) | No of Events (13) | KMM | OTHER | PU | 31 Dec 2024 |  |  |  | Pending